## Dashboard
FactSet × SWIB RAM — Tracker v04 (locked after 2026-04-29)
Project: swib_factset_ram ¦ Calls processed: 4 ¦ Topics: 14 (9 open active, 3 parked, 2 closed)
ID | Topic | Status | Importance | Created | Last update | Open follow-ups | Open questions
topic_001 | Risk model selection — LMAC vs MC Mac vs FV Mac | OPEN | HIGH | 2026-04-02 | 2026-04-29 | • Hassan: run LMAC vs MC Mac test on fixed-income portfolio (convexity check) • Nick: run FV Mac on fixed-income portfolio path for comparison • Nick: risk team to present pro/con analysis of LMAC vs MC Mac vs FV Mac on accuracy + report efficiency | • Are private markets covered under LMAC? • Which model is easiest to extend to fat-tail later? • Does FV Mac's caching layer change the memory profile vs MC Mac?
topic_003 | SO7 PA report build (A / B / L) | OPEN | HIGH | 2026-04-02 | 2026-04-29 | • Charlie: take SO1 + SO3 production docs and build single 'golden source' SO7 doc • Mark: send the SO2 production doc to Charlie • Louis: send Nick available times for the SO7 working group | • Which settings inconsistencies between SO1/SO2/SO3 (futures, currencies) must be fixed in the SO7 golden source? • Should risk-based performance attribution be dropped from SO7 given MC Mac limitation?
topic_004 | Stress test & scenario analysis build | OPEN | HIGH | 2026-04-02 | 2026-04-29 | • Nick: send Hassan the stress test test job file (Mark previously created, was meant to go last week) • Nick: follow up with questions on what's needed to get the stress test set up | • Will UDM composites coming over require modifications to current business lines?
topic_005 | Aggregated Risk Model (ARM) — CTF by account contributions | OPEN | HIGH | 2026-04-02 | 2026-04-29 | • FactSet: provide feedback on ARM PA report sent by SWIB | —
topic_006 | Composite & hierarchy uploads via parser | OPEN | MEDIUM | 2026-04-02 | 2026-04-29 | • Nick + Laura: test parser settings with sample examples before go-live • Charlie: use already-loaded ACTMs to generate interactive output once SO7 doc is built | • How are start/end dates for composite membership best structured in the daily file? • What templates does FactSet have for ACTM required fields and frequencies?
topic_007 | Snowflake data shares & environments | OPEN | MEDIUM | 2026-04-13 | 2026-04-29 | • Nick: leverage product team alongside himself + Charlie for SWIB-side Snowflake connectivity • Hassan: kick off introductory architecture discussion between teams • Louis: include 'when can FactSet push to Snowflake' in Smartsheet tracking | • Incremental delivery vs waterfall — wait until all data is ready, or push as it stabilizes?
topic_008 | Project tracking — Smartsheet vs FactSet implementation tracker | OPEN | MEDIUM | 2026-04-13 | 2026-04-20 | • Louis: meet with Anand to finalize Smartsheet structure • Louis: send first draft of Smartsheet to FactSet by EOD Tuesday after Apr 20 • FactSet: replicate SWIB's high-level topics in implementation tracker after receiving Smartsheet draft | —
topic_009 | Working group structure & cadence | OPEN | MEDIUM | 2026-04-20 | 2026-04-29 | • Louis + Hassan: discuss RAM sponsor meeting cadence offline | • How often should the RAM sponsor meeting run?
topic_010 | Standard Operating Procedures for daily EDS / EDS+ load | OPEN | MEDIUM | 2026-04-13 | 2026-04-13 | • Nick: ensure managed services receives heads-up on what's being built EDS-side • Hassan: share SOP framework with FactSet as it develops | • What rerun protocols must be in place for the EDS+ data going live?
topic_011 | Asset Allocation view (third hierarchy) | PARKED | LOW | 2026-04-02 | 2026-04-02 | — | • Should the Asset Allocation view be in this run or the next run?
topic_012 | Fat-tail & credit-adjusted VaR extensions | PARKED | LOW | 2026-04-02 | 2026-04-13 | — | • When should fat-tail modeling be revisited and what project milestone triggers the conversation?
topic_013 | Hedge-fund model — MSCI → FactSet mapping | PARKED | LOW | 2026-04-13 | 2026-04-13 | — | • How will SWIB's enhanced hedge-fund mapping be embedded into FactSet — via FPE or another mechanism?
topic_002 | Monte Carlo Mac memory failure | CLOSED | HIGH | 2026-04-02 | 2026-04-29 | — | —
topic_014 | Resourcing & implementation tracker access | CLOSED | LOW | 2026-04-02 | 2026-04-20 | • Courtney: order John McLeanHann a network ID for tracker access | —

## Chronology
Chronological updates per topic — verified against transcript history
Topic | 2026-04-02 | 2026-04-13 | 2026-04-20 | 2026-04-29 | RAG verification note
Risk model selection — LMAC vs MC Mac vs FV Mac [topic_001 · OPEN · HIGH] Which risk model the ARM run will use. LMAC favoured for 3-horizon views; MC Mac was the default but had memory issues now resolved; FV Mac proposed for caching benefits. Drives run efficiency and downstream extensibility to fat-tail / credit-adjusted VaR. | Raised. Hassan defaulted to MC Mac for ARM but flagged LMAC for 3-horizon views and FV Mac for caching. Nick committed to attack memory issue from 3 angles including FV Mac comparison. | Hassan reaffirmed LMAC appeal (Monte Carlo lacks 3-horizon views). Nick committed risk team to present a full pro/con on accuracy AND report efficiency. | Not discussed — meeting focused on Smartsheet alignment and SO7 build kickoff. | Mark indicated MC Mac is a viable option based on running the stress test document. Final model decision still gated on FactSet pro/con analysis. | Apr 2 transcript anchors the 3-model comparison framing; Apr 29 confirms MC Mac viability but does NOT close out LMAC/FV Mac comparison — verifier confirms decision remains open.
SO7 PA report build (A / B / L) [topic_003 · OPEN · HIGH] Building extended SO7 reports (A/B/L) replacing SO1/SO2/SO3 with added factor groupings, risk-based attribution, and broader analytics. Risk-based performance attribution is NOT possible under MC Mac so may be dropped. Prioritized as the lead workstream with dedicated weekly working group. | Hassan walked through SO1→SO7A, SO2→SO7B, SO3→SO7L mapping. Flagged SO7 as the most complex piece needing FactSet input. Mark to send starting doc. | Architecture re-walked with Charlie. Hassan confirmed SO7 is 'wish list' — risk-based performance attribution NOT possible under MC Mac, may be dropped. | Charlie to build golden source SO7 doc from SO1 + SO3 production docs; Mark to send SO2 doc. Will use already-loaded ACTMs for interactive output testing. | Prioritized as lead workstream. Dedicated weekly working group decided. Louis to coordinate times. Attendees: Mark, Sonon, Laura, Louis. | Continuous thread across all 4 calls. Verifier confirms no contradictions; status remains open with clear next actions concentrated on the working group kickoff.
Stress test & scenario analysis build [topic_004 · OPEN · HIGH] Monthly run, CTF grouped by business line and factors. SWIB has ~1.5 years of structure built; FactSet now reviewing for production-grade robustness. Holding off on dedicated working group until Charlie's feedback returns. | Hassan: stress test PA is 'ready' — grouped by business lines and factors, scenarios defined. Some business lines may need modification once UDM composites come over. | Hassan: ~1.5 years of work behind the structure; build is sound but lots of FactSet-related issues uncovered. Managed services engaged. Nick hit on the file with team that morning. | Mark to send SO1/SO3 PA paths for Charlie comparison. Nick reviewing the test job for go-forward setup. | Decision to hold off on dedicated working group — wait for FactSet feedback. Nick to send the test file and follow up with set-up questions. | Build is mature on SWIB side; bottleneck is FactSet review. Verifier confirms no working group is being scheduled yet — apparent inactivity on Apr 20 is consistent with parallel work, not abandonment.
Aggregated Risk Model (ARM) — CTF by account contributions [topic_005 · OPEN · HIGH] Daily run. Aggregate CTF/VTF/SMF by account contributions in FactSet, then join with hierarchies in Snowflake (not in FactSet). Replaces existing ExPost-based aggregation once private markets are modeled in FactSet via EMAC. Viewed as straightforward once memory boost issue resolved. | Hassan introduced 'aggregate outside FactSet' approach — run CTF by account contributions only, join with hierarchies in Snowflake. Replaces ExPost-based aggregation once EMAC delivers private markets in FactSet. | Architecture restated with Charlie. Hassan confirmed limited risk metrics on purpose — broader metrics live in Portfolio Risk Analytics. | No specific ARM updates — work continuing on upstream composite uploads. | Hassan: ARM is 'pretty straightforward once we address memory boost.' Waiting on FactSet feedback; will arrange call when received. No dedicated working group yet. | Memory boost dependency now resolved (Topic 002). Verifier confirms ARM remains open pending FactSet review of the SWIB-built ARM PA, not pending technical blockers.
Composite & hierarchy uploads via parser [topic_006 · OPEN · MEDIUM] Daily uploads of business lines, sub-BL, AC1/AC2 composites + ACTMs + benchmarks sourced from UDM. Parser will use 'matching start date' setting for incremental updates. ACTMs already loaded as samples. Replaces SWIB's current monthly 'core aim' manual process. | Hassan flagged need for robust daily-update process for accounts, composites, benchmarks. Mark already started composite setup work. | Laura walked through composite structure work-in-progress. Parser 'matching start date' setting decided. Section 3 (replacing core aim) tied to internal UDM project. | ACTMs already loaded as samples. Troy flagged: flat files build + standup is the first concrete priority for the team. | Charlie continuing report-creation work; hierarchy setup is upstream — 'once the composite hierarchy gets set up, then we can actually start putting these through the reports.' | Continuous progress thread; parser setting decision is locked. Verifier confirms downstream dependency (SO7 reports waiting on hierarchies).
Snowflake data shares & environments [topic_007 · OPEN · MEDIUM] Onboarding FactSet Snowflake data shares across SWIB dev/test/UAT/prod environments. Independent workstream from SO7. Architecture-team-to-architecture-team contact pending. Data delivery comes only after PA engine output is validated. | Not raised explicitly — architecture diagram only mentioned Snowflake as downstream target. | Anand flagged need for dev/test/UAT/prod environments and a FactSet technology contact for SWIB's Snowflake architects. Nick to leverage product team. | Louis: when can FactSet start pushing data? Nick's position: only after PA engine output is validated; flat-file structure stabilizes first. | Hassan to kick off introductory architecture discussion — independent workstream, won't block SO7. | Topic created Apr 13, not Apr 2. Verifier confirms Apr 2 had only passing reference, not enough for topic creation per the rubric. Apr 13 is the legitimate origin.
Project tracking — Smartsheet vs FactSet implementation tracker [topic_008 · OPEN · MEDIUM] Aligning SWIB's Smartsheet (covering full charter incl. Power BI) with FactSet's implementation tracker (SOW-specific). SWIB tracks at module level; FactSet tracks granular. First draft of Smartsheet to FactSet by EOD Tuesday after Apr 20. | Not raised. | Hassan: SWIB Smartsheet exists, will integrate FactSet workstream tasks; Louis to update Smartsheet based on FactSet discussions. | Decision on hierarchy alignment locked. Louis-Anand meeting scheduled. Timeline: first draft EOM April, final view early May. | Not explicitly re-raised. | Verifier: Apr 29 absence is consistent with parallel work on Smartsheet draft, not abandonment. Status remains open.
Working group structure & cadence [topic_009 · OPEN · MEDIUM] Monday RAM weekly call stays as umbrella sync. Working groups are ad-hoc EXCEPT SO7 which gets a fixed weekly slot. Mark cannot be in all 3 deep-dive groups simultaneously — explicit constraint. | Not raised — only weekly Monday 11am Central agreed. | Not raised explicitly. | Hassan: weekly RAM call should evolve into summary cadence; deep-dive work shifts to working groups (ARM, stress test, SO7, BAU). Sponsor meeting frequency taken offline. | Decisions locked: Monday RAM stays umbrella, SO7 gets fixed slot, others ad-hoc. Each working group starts with full-group kickoff. Mark cannot attend all 3 deep-dives simultaneously. | Verifier confirms Mark's constraint is explicit in Apr 29 transcript ('Mark cannot be in all three of them').
Standard Operating Procedures for daily EDS / EDS+ load [topic_010 · OPEN · MEDIUM] Framework being developed in parallel with managed services. Must work for current EDS and forward EDS+ load. Cross-communication needed with RAM workstream so optimization requirements feed in. | Not raised. | Hassan: SOP framework being developed in parallel with managed services; cross-comm needed with RAM workstream for optimization requirements. Nick to coordinate. | Not specifically raised. | Not raised. | STALE candidate — not raised in last 2 calls. Status review pass should flag this for explicit human decision (keep open / park / merge into another topic).
Asset Allocation view (third hierarchy) [topic_011 · PARKED · LOW] A third grouping view (alongside business line + asset class) matching SWIB's actual asset allocation, requiring new composites (AA1, AA2, AA3...). Parked for future round. | Hassan raised future need (triggered by Anand's reminder). No owner, no commitment, explicitly 'keep in mind.' | Not re-raised. | Not re-raised. | Not re-raised. | PARKED. No mentions across 3 subsequent calls. Verifier confirms parked status.
Fat-tail & credit-adjusted VaR extensions [topic_012 · PARKED · LOW] Future model enhancements beyond the current MC Mac baseline. Credit-adjusted VaR via FactSet's CRYAT team explicitly deferred to a future phase. | Hassan: stay with MC Mac for now; 'at some point probably move to the fat tail.' Flagged extensibility as a model-selection criterion. | Hassan: credit-adjusted VaR via CRYAT team is 'not for this time around — once the platform is established, these will be enhancements we may work on.' | Not re-raised. | Not re-raised. | PARKED with explicit deferral decision. Verifier links open question on fat-tail back to Topic 001 (model selection criteria — extensibility).
Hedge-fund model — MSCI → FactSet mapping [topic_013 · PARKED · LOW] Today: linear MSCI-driven mapping into FactSet. Future: explore non-linear / ML mapping delivered via FactSet's FPE. Explicitly parked for future exploration. | Not raised. | Hassan: risk team developing enhanced mapping (potentially ML); will need to discuss with FactSet for FPE embedding — 'something we will explore in the future, not now.' | Not re-raised. | Not re-raised. | PARKED. Single mention in Apr 13 with explicit deferral language.
Monte Carlo Mac memory failure [topic_002 · CLOSED · HIGH] Mark's CTF-by-account MC Mac job crashed even with one risk metric due to insufficient memory. Memory boost option resolved it — confirmed by PA product team re-running Mark's test job on Apr 13. | Mark's MC Mac job crashed even with 1 risk metric (volatility contribution). Managed services confirmed memory failure in both Batcher and PA. Nick to attack from 3 angles. | RESOLVED. Nick met with PA product team that morning; they ran Mark's test job with memory boost and it completed. | Not re-raised. | Hassan and Mark referenced the memory-boost fix as resolved; ARM viewed as straightforward 'once we address the memory boost issue we talked about.' | Apr 13 transcript contains explicit closure: 'they did take Mark's test job and run it and it did complete with the memory boost.' Verifier confirms status=closed.
Resourcing & implementation tracker access [topic_014 · CLOSED · LOW] Charlie Moss assigned as FactSet implementation lead. SWIB-side access to FactSet's implementation tracker confirmed. John McLeanHann to receive network ID. | Charlie Moss assigned. Joins from Apr 13. Apr 7 call cancelled. | Charlie attended first call. SWIB-side tracker access confirmed. Courtney to order John's network ID. | Implementation tracker access in place; focus shifted to Smartsheet alignment (Topic 008). | Not re-raised. | CLOSED. Core resourcing decisions completed; only John's network ID remains as an open admin task within an otherwise closed topic.

## Anchors lifecycle
Anchor lifecycle — follow-up items and open questions with status tracking
Topic | Type | Item | Owner | Added in | Status | Closed in
Risk model selection — LMAC vs MC Mac vs FV Mac | Follow-up | Hassan: run LMAC vs MC Mac test on fixed-income portfolio (convexity check) | Hassan | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Follow-up | Nick: run FV Mac on fixed-income portfolio path for comparison | Nick | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Follow-up | Nick: risk team to present pro/con analysis of LMAC vs MC Mac vs FV Mac on accuracy + report efficiency | Nick | 2026-04-13 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Open question | Are private markets covered under LMAC? | — | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Open question | Which model is easiest to extend to fat-tail later? | — | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Open question | Does FV Mac's caching layer change the memory profile vs MC Mac? | — | 2026-04-02 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | Mark: send SO7 starting document to Nick | Mark | 2026-04-02 | DONE | 2026-04-13
SO7 PA report build (A / B / L) | Follow-up | Charlie: take SO1 + SO3 production docs and build single 'golden source' SO7 doc | Charlie | 2026-04-20 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | Mark: send the SO2 production doc to Charlie | Mark | 2026-04-20 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | Louis: send Nick available times for the SO7 working group | Louis | 2026-04-29 | OPEN | —
SO7 PA report build (A / B / L) | Open question | Which settings inconsistencies between SO1/SO2/SO3 (futures, currencies) must be fixed in the SO7 golden source? | — | 2026-04-13 | OPEN | —
SO7 PA report build (A / B / L) | Open question | Should risk-based performance attribution be dropped from SO7 given MC Mac limitation? | — | 2026-04-13 | OPEN | —
Stress test & scenario analysis build | Follow-up | Nick: send Hassan the stress test test job file (Mark previously created, was meant to go last week) | Nick | 2026-04-29 | OPEN | —
Stress test & scenario analysis build | Follow-up | Nick: follow up with questions on what's needed to get the stress test set up | Nick | 2026-04-29 | OPEN | —
Stress test & scenario analysis build | Open question | Will UDM composites coming over require modifications to current business lines? | — | 2026-04-02 | OPEN | —
Aggregated Risk Model (ARM) — CTF by account contributions | Follow-up | FactSet: provide feedback on ARM PA report sent by SWIB | FactSet | 2026-04-13 | OPEN | —
Composite & hierarchy uploads via parser | Follow-up | Nick + Laura: test parser settings with sample examples before go-live | Nick + Laura | 2026-04-13 | OPEN | —
Composite & hierarchy uploads via parser | Follow-up | Charlie: use already-loaded ACTMs to generate interactive output once SO7 doc is built | Charlie | 2026-04-20 | OPEN | —
Composite & hierarchy uploads via parser | Open question | How are start/end dates for composite membership best structured in the daily file? | — | 2026-04-13 | OPEN | —
Composite & hierarchy uploads via parser | Open question | What templates does FactSet have for ACTM required fields and frequencies? | — | 2026-04-13 | OPEN | —
Snowflake data shares & environments | Follow-up | Nick: leverage product team alongside himself + Charlie for SWIB-side Snowflake connectivity | Nick | 2026-04-13 | OPEN | —
Snowflake data shares & environments | Follow-up | Hassan: kick off introductory architecture discussion between teams | Hassan | 2026-04-29 | OPEN | —
Snowflake data shares & environments | Follow-up | Louis: include 'when can FactSet push to Snowflake' in Smartsheet tracking | Louis | 2026-04-20 | OPEN | —
Snowflake data shares & environments | Open question | Incremental delivery vs waterfall — wait until all data is ready, or push as it stabilizes? | — | 2026-04-20 | OPEN | —
Project tracking — Smartsheet vs FactSet implementation tracker | Follow-up | Louis: meet with Anand to finalize Smartsheet structure | Louis | 2026-04-20 | OPEN | —
Project tracking — Smartsheet vs FactSet implementation tracker | Follow-up | Louis: send first draft of Smartsheet to FactSet by EOD Tuesday after Apr 20 | Louis | 2026-04-20 | OPEN | —
Project tracking — Smartsheet vs FactSet implementation tracker | Follow-up | FactSet: replicate SWIB's high-level topics in implementation tracker after receiving Smartsheet draft | FactSet (Nick) | 2026-04-20 | OPEN | —
Working group structure & cadence | Follow-up | Louis + Hassan: discuss RAM sponsor meeting cadence offline | Louis + Hassan | 2026-04-20 | OPEN | —
Working group structure & cadence | Open question | How often should the RAM sponsor meeting run? | — | 2026-04-20 | OPEN | —
Standard Operating Procedures for daily EDS / EDS+ load | Follow-up | Nick: ensure managed services receives heads-up on what's being built EDS-side | Nick | 2026-04-13 | OPEN | —
Standard Operating Procedures for daily EDS / EDS+ load | Follow-up | Hassan: share SOP framework with FactSet as it develops | Hassan | 2026-04-13 | OPEN | —
Standard Operating Procedures for daily EDS / EDS+ load | Open question | What rerun protocols must be in place for the EDS+ data going live? | — | 2026-04-13 | OPEN | —
Asset Allocation view (third hierarchy) | Open question | Should the Asset Allocation view be in this run or the next run? | — | 2026-04-02 | OPEN | —
Fat-tail & credit-adjusted VaR extensions | Open question | When should fat-tail modeling be revisited and what project milestone triggers the conversation? | — | 2026-04-02 | OPEN | —
Hedge-fund model — MSCI → FactSet mapping | Open question | How will SWIB's enhanced hedge-fund mapping be embedded into FactSet — via FPE or another mechanism? | — | 2026-04-13 | OPEN | —
Monte Carlo Mac memory failure | Follow-up | Mark: send PA document to Nick for memory issue investigation | Mark | 2026-04-02 | DONE | 2026-04-02
Monte Carlo Mac memory failure | Follow-up | Nick: attack memory issue from 3 angles — setup change, alternate model, memory boost | Nick | 2026-04-02 | DONE | 2026-04-13
Resourcing & implementation tracker access | Follow-up | Courtney: order John McLeanHann a network ID for tracker access | Courtney | 2026-04-13 | OPEN | —
Resourcing & implementation tracker access | Follow-up | Nick: send Louis the tracker link (workstation + web access) | Nick | 2026-04-13 | DONE | 2026-04-13

## Decisions log
Decisions log — every locked decision across all calls
Topic | Decision | Decided in
Aggregated Risk Model (ARM) — CTF by account contributions | Aggregation across business lines / sub-BL / AC1-AC3 happens in Snowflake, NOT FactSet | 2026-04-02
Resourcing & implementation tracker access | Charlie Moss assigned by FactSet professional services as implementation lead | 2026-04-02
Resourcing & implementation tracker access | Apr 7 call cancelled to give Charlie prep time; weekly cadence resumes Apr 13 | 2026-04-02
Monte Carlo Mac memory failure | Memory boost resolves the MC Mac memory failure for Mark's test case | 2026-04-13
Composite & hierarchy uploads via parser | Parser will use 'matching start date' setting — incremental updates, not full overwrite. Rejoining a composite creates a second start-date entry. | 2026-04-13
Fat-tail & credit-adjusted VaR extensions | Credit-adjusted VaR and fat-tail extensions are deferred to a future phase (post-platform-establishment) | 2026-04-13
SO7 PA report build (A / B / L) | SO1→SO7A, SO2→SO7B, SO3→SO7L naming confirmed | 2026-04-20
Snowflake data shares & environments | Data delivery to Snowflake happens AFTER PA engine output is validated; flat-file structure stabilizes first | 2026-04-20
Project tracking — Smartsheet vs FactSet implementation tracker | SWIB Smartsheet stays one or two levels above FactSet tracker. SWIB tracks ARM / stress test / portfolio risk analytics at module level; FactSet stays granular. | 2026-04-20
SO7 PA report build (A / B / L) | SO7 is the priority workstream — gets a dedicated weekly working group | 2026-04-29
SO7 PA report build (A / B / L) | Working group attendees: Mark, Sonon, Laura, Louis | 2026-04-29
Stress test & scenario analysis build | Hold off on a dedicated stress test working group — wait for Charlie's feedback first | 2026-04-29
Aggregated Risk Model (ARM) — CTF by account contributions | Hold off on dedicated ARM working group — wait for FactSet feedback first | 2026-04-29
Snowflake data shares & environments | Hassan to kick off introductory architecture discussion soon — independent workstream, won't block SO7 | 2026-04-29
Working group structure & cadence | Monday RAM weekly call stays as umbrella sync | 2026-04-29
Working group structure & cadence | SO7 working group gets a fixed weekly slot; others are ad-hoc | 2026-04-29
Working group structure & cadence | Each working group has an initial full-group kickoff meeting to agree direction, then splits off | 2026-04-29

## Key terms registry
Key terms registry — anchor for matcher + RAG retrieval queries
These terms uniquely identify each topic in transcripts. Used by the matcher (Step B) for sharper match decisions and by the verifier (Step C) to build retrieval queries.
ID | Topic | Key terms | Term count
topic_001 | Risk model selection — LMAC vs MC Mac vs FV Mac | LMAC, MC Mac, FV Mac, Monte Carlo, fair value Mac, fixed income convexity, Hassan, Nick, risk model, short term medium term long term | 10
topic_003 | SO7 PA report build (A / B / L) | SO7, SO7A, SO7B, SO7L, SO1, SO2, SO3, golden source, Charlie, factor groupings, risk-based performance attribution, wish list | 12
topic_004 | Stress test & scenario analysis build | stress test, scenario analysis, monthly run, CTF business line factors, test job, Mark | 6
topic_005 | Aggregated Risk Model (ARM) — CTF by account contributions | ARM, aggregated risk model, CTF, VTF, SMF, account contributions, Snowflake aggregation, business line sub-business line AC1 AC2 AC3, ExPost, EMAC | 10
topic_006 | Composite & hierarchy uploads via parser | composite, hierarchy, parser, ACTM, benchmarks, UDM, start date, end date, matching start date, core aim, daily upload, Laura | 12
topic_007 | Snowflake data shares & environments | Snowflake, data shares, dev test UAT prod, environments, architecture team, Anand, data engineering, waterfall | 8
topic_008 | Project tracking — Smartsheet vs FactSet implementation tracker | Smartsheet, implementation tracker, charter, Power BI, module level, Louis, Anand | 7
topic_009 | Working group structure & cadence | working group, RAM weekly call, Monday call, sponsor meeting, ad hoc, deep dive | 6
topic_010 | Standard Operating Procedures for daily EDS / EDS+ load | SOP, standard operating procedures, EDS, EDS+, rerun protocol, managed services, daily load | 7
topic_011 | Asset Allocation view (third hierarchy) | asset allocation view, AA1, AA2, AA3, third hierarchy, Anand | 6
topic_012 | Fat-tail & credit-adjusted VaR extensions | fat-tail, credit-adjusted VaR, CRYAT team, MC Mac extension | 4
topic_013 | Hedge-fund model — MSCI → FactSet mapping | hedge fund, MSCI, FactSet mapping, FPE, non-linear, machine learning | 6
topic_002 | Monte Carlo Mac memory failure | MC Mac, memory, memory boost, Batcher, PA, volatility contribution, managed services, Mark | 8
topic_014 | Resourcing & implementation tracker access | Charlie Moss, professional services, implementation tracker, John McLeanHann, network ID, Courtney | 6

## Status review
Status review — stale-topic & integrity flags for human decision
Run periodically (every 4-5 calls or on demand). Surfaces topics not touched recently and items needing explicit closure. Never auto-closes — only flags.
Topic | Current status | Last touched | Calls silent | Recommendation
Risk model selection — LMAC vs MC Mac vs FV Mac | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
SO7 PA report build (A / B / L) | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
Stress test & scenario analysis build | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
Aggregated Risk Model (ARM) — CTF by account contributions | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
Composite & hierarchy uploads via parser | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
Snowflake data shares & environments | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
Project tracking — Smartsheet vs FactSet implementation tracker | OPEN | 2026-04-20 | 1 | Silent 1 call — likely active, no action.
Working group structure & cadence | OPEN | 2026-04-29 | 0 | Active in latest call — no action.
Standard Operating Procedures for daily EDS / EDS+ load | OPEN | 2026-04-13 | 2 | FLAG: Silent 2 calls. Confirm still active or park.
Asset Allocation view (third hierarchy) | PARKED | 2026-04-02 | 3 | Parked and silent ≥ 2 calls — keep parked, surface next review only on explicit revival.
Fat-tail & credit-adjusted VaR extensions | PARKED | 2026-04-13 | 2 | Parked and silent ≥ 2 calls — keep parked, surface next review only on explicit revival.
Hedge-fund model — MSCI → FactSet mapping | PARKED | 2026-04-13 | 2 | Parked and silent ≥ 2 calls — keep parked, surface next review only on explicit revival.
Monte Carlo Mac memory failure | CLOSED | 2026-04-29 | 0 | Closed — no action needed.
Resourcing & implementation tracker access | CLOSED | 2026-04-20 | 1 | Closed — no action needed.