## Dashboard
FactSet × SWIB RAM — Tracker v05 (locked after 2026-05-18)
Project: swib_factset_ram ¦ Calls processed: 5 ¦ Topics: 14 (9 open active, 3 parked, 2 closed)
ID | Topic | Status | Importance | Created | Last update | Open follow-ups | Open questions
topic_001 | Risk model selection — LMAC vs MC Mac vs FV Mac | OPEN | HIGH | 2026-04-02 | 2026-04-29 | • Hassan: run LMAC vs MC Mac test on fixed-income portfolio (convexity check) • Nick: run FV Mac on fixed-income portfolio path for comparison • Nick: risk team to present pro/con analysis of LMAC vs MC Mac vs FV Mac on accuracy + report efficiency | • Are private markets covered under LMAC? • Which model is easiest to extend to fat-tail later? • Does FV Mac's caching layer change the memory profile vs MC Mac?
topic_003 | SO7 PA report build (A / B / L) | OPEN | HIGH | 2026-04-02 | 2026-05-18 | • Mark + Charlie + Sean: review each report in the combined SO7 doc to confirm correct stress test scenarios • Charlie: provide data coverage check on SO7 columns once SWIB confirms which columns to assess • Hassan + Mark + Sean: rationalize SO7 column scope — confirm which metrics keep, which to drop, which alternatives FactSet offers • FactSet (Nick + Charlie): document available structural data for CLOs, CMBS, ABS by public CUSIP / ticker • FactSet (Nick + Charlie): document available options Greeks coverage for SO7 | • Which settings inconsistencies between SO1/SO2/SO3 (futures, currencies) must be fixed in the SO7 golden source? • Should risk-based performance attribution be dropped from SO7 given MC Mac limitation? • What structural data is available in FactSet for CLOs, CMBS, ABS with public identifiers? • Which Greeks does FactSet provide for options in SO7? • If SWIB adds significantly more columns, will SO7 PA jobs still complete or need to be redesigned into multiple tasks?
topic_004 | Stress test & scenario analysis build | OPEN | HIGH | 2026-04-02 | 2026-05-18 | • Nick: send Hassan the stress test test job file (Mark previously created, was meant to go last week) • Nick: follow up with questions on what's needed to get the stress test set up • Charlie: ping Mark to review the combined stress test doc and confirm scenario alignment • Mark: review combined stress test doc and confirm each report uses correct scenarios | • Will UDM composites coming over require modifications to current business lines?
topic_005 | Aggregated Risk Model (ARM) — CTF by account contributions | OPEN | HIGH | 2026-04-02 | 2026-05-18 | • FactSet: provide feedback on ARM PA report sent by SWIB • Hassan: secure a large-file transfer method and send ARM file to Nick | —
topic_006 | Composite & hierarchy uploads via parser | OPEN | MEDIUM | 2026-04-02 | 2026-04-29 | • Nick + Laura: test parser settings with sample examples before go-live • Charlie: use already-loaded ACTMs to generate interactive output once SO7 doc is built | • How are start/end dates for composite membership best structured in the daily file? • What templates does FactSet have for ACTM required fields and frequencies?
topic_007 | Snowflake data shares & environments | OPEN | MEDIUM | 2026-04-13 | 2026-05-18 | • Nick: leverage product team alongside himself + Charlie for SWIB-side Snowflake connectivity • Louis: include 'when can FactSet push to Snowflake' in Smartsheet tracking | • Incremental delivery vs waterfall — wait until all data is ready, or push as it stabilizes?
topic_008 | Project tracking — Smartsheet vs FactSet implementation tracker | OPEN | MEDIUM | 2026-04-13 | 2026-04-20 | • Louis: meet with Anand to finalize Smartsheet structure • Louis: send first draft of Smartsheet to FactSet by EOD Tuesday after Apr 20 • FactSet: replicate SWIB's high-level topics in implementation tracker after receiving Smartsheet draft | —
topic_009 | Working group structure & cadence | OPEN | MEDIUM | 2026-04-20 | 2026-05-18 | • Louis + Hassan: discuss RAM sponsor meeting cadence offline | • How often should the RAM sponsor meeting run?
topic_010 | Standard Operating Procedures for daily EDS / EDS+ load | OPEN | MEDIUM | 2026-04-13 | 2026-04-13 | • Nick: ensure managed services receives heads-up on what's being built EDS-side • Hassan: share SOP framework with FactSet as it develops | • What rerun protocols must be in place for the EDS+ data going live?
topic_011 | Asset Allocation view (third hierarchy) | PARKED | LOW | 2026-04-02 | 2026-04-02 | — | • Should the Asset Allocation view be in this run or the next run?
topic_012 | Fat-tail & credit-adjusted VaR extensions | PARKED | LOW | 2026-04-02 | 2026-04-13 | — | • When should fat-tail modeling be revisited and what project milestone triggers the conversation?
topic_013 | Hedge-fund model — MSCI → FactSet mapping | PARKED | LOW | 2026-04-13 | 2026-04-13 | — | • How will SWIB's enhanced hedge-fund mapping be embedded into FactSet — via FPE or another mechanism?
topic_002 | Monte Carlo Mac memory failure | CLOSED | HIGH | 2026-04-02 | 2026-04-29 | — | —
topic_014 | Resourcing & implementation tracker access | CLOSED | LOW | 2026-04-02 | 2026-04-20 | • Courtney: order John McLeanHann a network ID for tracker access | —

## Chronology
Chronological updates per topic — verified against transcript history
Topic | 2026-04-02 | 2026-04-13 | 2026-04-20 | 2026-04-29 | 2026-05-18 | RAG verification note
Risk model selection — LMAC vs MC Mac vs FV Mac [topic_001 · OPEN · HIGH] Which risk model the ARM run will use. LMAC favoured for 3-horizon views; MC Mac was the default but had memory issues now resolved; FV Mac proposed for caching benefits. Drives run efficiency and downstream extensibility to fat-tail / credit-adjusted VaR. | Raised. Hassan defaulted to MC Mac for ARM but flagged LMAC for 3-horizon views and FV Mac for caching. Nick committed to attack memory issue from 3 angles including FV Mac comparison. | Hassan reaffirmed LMAC appeal (Monte Carlo lacks 3-horizon views). Nick committed risk team to present a full pro/con on accuracy AND report efficiency. | Not discussed — meeting focused on Smartsheet alignment and SO7 build kickoff. | Mark indicated MC Mac is a viable option based on running the stress test document. Final model decision still gated on FactSet pro/con analysis. | Not discussed. | Apr 2 transcript anchors the 3-model comparison framing; Apr 29 confirms MC Mac viability but does NOT close out LMAC/FV Mac comparison — verifier confirms decision remains open.
SO7 PA report build (A / B / L) [topic_003 · OPEN · HIGH] Building extended SO7 reports (A/B/L) replacing SO1/SO2/SO3 with added factor groupings, risk-based attribution, and broader analytics. Combined golden-source doc built by Charlie; sample composite ready for test runs. Current spec ~75% of final scope — column rationalization phase next, with FactSet input needed on CLO/CMBS/ABS structural data, options Greeks, and factor grouping. Weekly working group active (Mark, Sonon, Laura, Louis, Sean). | Hassan walked through SO1→SO7A, SO2→SO7B, SO3→SO7L mapping. Flagged SO7 as the most complex piece needing FactSet input. Mark to send starting doc. | Architecture re-walked with Charlie. Hassan confirmed SO7 is 'wish list' — risk-based performance attribution NOT possible under MC Mac, may be dropped. | Charlie to build golden source SO7 doc from SO1 + SO3 production docs; Mark to send SO2 doc. Will use already-loaded ACTMs for interactive output testing. | Prioritized as lead workstream. Dedicated weekly working group decided. Louis to coordinate times. Attendees: Mark, Sonon, Laura, Louis. | Charlie has combined three PA docs into one with three sections: SO1 collapsed with Mac model, SO2 collapsed with BARRA model, SO3 expanded with Mac model. Mark sent a sample composite with mixed asset types for running through all reports. Next step is column rationalization — Hassan flagged the need to assess what fields in the current SO7 spec are needed vs. should change. Discussion to include CLO / CMBS / ABS structural data availability, options Greeks coverage, and factor grouping approach. Sean Won added to the SO7 working group. SO7 is ~75% of what SWIB wants, 25% reserved for FactSet-suggested changes. Mark absent today; substantive review deferred until he returns tomorrow. | Continuous thread across all 4 calls. Verifier confirms no contradictions; status remains open with clear next actions concentrated on the working group kickoff.
Stress test & scenario analysis build [topic_004 · OPEN · HIGH] Monthly run, CTF grouped by business line and factors. Composites received by FactSet. Mark's three PA files combined into one doc by Charlie; awaiting Mark's review to confirm correct stress scenarios per report. SWIB structure remains mature; bottleneck is Mark's review turnaround. | Hassan: stress test PA is 'ready' — grouped by business lines and factors, scenarios defined. Some business lines may need modification once UDM composites come over. | Hassan: ~1.5 years of work behind the structure; build is sound but lots of FactSet-related issues uncovered. Managed services engaged. Nick hit on the file with team that morning. | Mark to send SO1/SO3 PA paths for Charlie comparison. Nick reviewing the test job for go-forward setup. | Decision to hold off on dedicated working group — wait for FactSet feedback. Nick to send the test file and follow up with set-up questions. | Composites received by FactSet. Mark sent three PA files representing the full set. Charlie combined those three into one doc and asked Mark to review each report to confirm correct stress test scenarios — no response yet from Mark. Charlie will ping Mark on the thread. No new action gates; waiting on Mark's review of the combined doc. | Build is mature on SWIB side; bottleneck is FactSet review. Verifier confirms no working group is being scheduled yet — apparent inactivity on Apr 20 is consistent with parallel work, not abandonment.
Aggregated Risk Model (ARM) — CTF by account contributions [topic_005 · OPEN · HIGH] Daily run. Aggregate CTF/VTF/SMF by account contributions in FactSet, then join with hierarchies in Snowflake. SWIB has the ARM file ready for FactSet but transfer is blocked on a large-file delivery method. FactSet feedback remains owed but is now downstream of the file delivery. | Hassan introduced 'aggregate outside FactSet' approach — run CTF by account contributions only, join with hierarchies in Snowflake. Replaces ExPost-based aggregation once EMAC delivers private markets in FactSet. | Architecture restated with Charlie. Hassan confirmed limited risk metrics on purpose — broader metrics live in Portfolio Risk Analytics. | No specific ARM updates — work continuing on upstream composite uploads. | Hassan: ARM is 'pretty straightforward once we address memory boost.' Waiting on FactSet feedback; will arrange call when received. No dedicated working group yet. | Status reversed: SWIB now has the ARM file ready for Nick, but transfer is blocked — file is too large for normal channels and Hassan is working on access to an alternate delivery method. Once delivered, FactSet can begin processing and provide feedback. No new content review until file lands. | Memory boost dependency now resolved (Topic 002). Verifier confirms ARM remains open pending FactSet review of the SWIB-built ARM PA, not pending technical blockers.
Composite & hierarchy uploads via parser [topic_006 · OPEN · MEDIUM] Daily uploads of business lines, sub-BL, AC1/AC2 composites + ACTMs + benchmarks sourced from UDM. Parser will use 'matching start date' setting for incremental updates. ACTMs already loaded as samples. Replaces SWIB's current monthly 'core aim' manual process. | Hassan flagged need for robust daily-update process for accounts, composites, benchmarks. Mark already started composite setup work. | Laura walked through composite structure work-in-progress. Parser 'matching start date' setting decided. Section 3 (replacing core aim) tied to internal UDM project. | ACTMs already loaded as samples. Troy flagged: flat files build + standup is the first concrete priority for the team. | Charlie continuing report-creation work; hierarchy setup is upstream — 'once the composite hierarchy gets set up, then we can actually start putting these through the reports.' | Implicit progress — composites referenced as already received by FactSet for stress test work. No specific parser/hierarchy discussion in this call. | Continuous progress thread; parser setting decision is locked. Verifier confirms downstream dependency (SO7 reports waiting on hierarchies).
Snowflake data shares & environments [topic_007 · OPEN · MEDIUM] Onboarding FactSet Snowflake data shares across SWIB dev/test/UAT/prod environments. Kickoff complete; working group active. Test upload of SO7 output to Snowflake achievable once SWIB-side file specs are finalized. Independent workstream, not blocking SO7. | Not raised explicitly — architecture diagram only mentioned Snowflake as downstream target. | Anand flagged need for dev/test/UAT/prod environments and a FactSet technology contact for SWIB's Snowflake architects. Nick to leverage product team. | Louis: when can FactSet start pushing data? Nick's position: only after PA engine output is validated; flat-file structure stabilizes first. | Hassan to kick off introductory architecture discussion — independent workstream, won't block SO7. | Kickoff meeting for the Snowflake data share onboarding occurred. Working group now active. Charlie's SO7 test documents are ready to be productionalized for a test upload to Snowflake whenever the SWIB-side specs are finalized. Snowflake counted as one of the four kicked-off working groups. | Topic created Apr 13, not Apr 2. Verifier confirms Apr 2 had only passing reference, not enough for topic creation per the rubric. Apr 13 is the legitimate origin.
Project tracking — Smartsheet vs FactSet implementation tracker [topic_008 · OPEN · MEDIUM] Aligning SWIB's Smartsheet (covering full charter incl. Power BI) with FactSet's implementation tracker (SOW-specific). SWIB tracks at module level; FactSet tracks granular. First draft of Smartsheet to FactSet by EOD Tuesday after Apr 20. | Not raised. | Hassan: SWIB Smartsheet exists, will integrate FactSet workstream tasks; Louis to update Smartsheet based on FactSet discussions. | Decision on hierarchy alignment locked. Louis-Anand meeting scheduled. Timeline: first draft EOM April, final view early May. | Not explicitly re-raised. | Not explicitly raised in this call. | Verifier: Apr 29 absence is consistent with parallel work on Smartsheet draft, not abandonment. Status remains open.
Working group structure & cadence [topic_009 · OPEN · MEDIUM] Four working groups active: SO7 (highest priority, weekly), stress test, Snowflake onboarding, ARM. Monday RAM call is a half-hour cross-stream umbrella. BAU working group deferred until build is further along. Resource overlap means people may focus single-stream in a given week. | Not raised — only weekly Monday 11am Central agreed. | Not raised explicitly. | Hassan: weekly RAM call should evolve into summary cadence; deep-dive work shifts to working groups (ARM, stress test, SO7, BAU). Sponsor meeting frequency taken offline. | Decisions locked: Monday RAM stays umbrella, SO7 gets fixed slot, others ad-hoc. Each working group starts with full-group kickoff. Mark cannot attend all 3 deep-dives simultaneously. | Four working groups now formally kicked off: SO7, stress test, Snowflake onboarding, ARM. Monday RAM call shortened to a half-hour weekly umbrella sync for cross-stream progress check-ins. SO7 confirmed as the highest-priority stream with weekly cadence. Other streams meet on a rolling basis based on momentum rather than fixed weekly slots. Resource overlap acknowledged — same people may need to focus on one workstream for a whole week. | Verifier confirms Mark's constraint is explicit in Apr 29 transcript ('Mark cannot be in all three of them').
Standard Operating Procedures for daily EDS / EDS+ load [topic_010 · OPEN · MEDIUM] Framework being developed in parallel with managed services. Must work for current EDS and forward EDS+ load. Cross-communication needed with RAM workstream so optimization requirements feed in. | Not raised. | Hassan: SOP framework being developed in parallel with managed services; cross-comm needed with RAM workstream for optimization requirements. Nick to coordinate. | Not specifically raised. | Not raised. | Not raised. Topic now silent for 3 consecutive calls (Apr 20, Apr 29, May 18) — flag for explicit human decision (keep open / park / merge into another topic). | STALE candidate — not raised in last 2 calls. Status review pass should flag this for explicit human decision (keep open / park / merge into another topic).
Asset Allocation view (third hierarchy) [topic_011 · PARKED · LOW] A third grouping view (alongside business line + asset class) matching SWIB's actual asset allocation, requiring new composites (AA1, AA2, AA3...). Parked for future round. | Hassan raised future need (triggered by Anand's reminder). No owner, no commitment, explicitly 'keep in mind.' | Not re-raised. | Not re-raised. | Not re-raised. | Not re-raised. Remains parked. | PARKED. No mentions across 3 subsequent calls. Verifier confirms parked status.
Fat-tail & credit-adjusted VaR extensions [topic_012 · PARKED · LOW] Future model enhancements beyond the current MC Mac baseline. Credit-adjusted VaR via FactSet's CRYAT team explicitly deferred to a future phase. | Hassan: stay with MC Mac for now; 'at some point probably move to the fat tail.' Flagged extensibility as a model-selection criterion. | Hassan: credit-adjusted VaR via CRYAT team is 'not for this time around — once the platform is established, these will be enhancements we may work on.' | Not re-raised. | Not re-raised. | Not re-raised. Remains parked. | PARKED with explicit deferral decision. Verifier links open question on fat-tail back to Topic 001 (model selection criteria — extensibility).
Hedge-fund model — MSCI → FactSet mapping [topic_013 · PARKED · LOW] Today: linear MSCI-driven mapping into FactSet. Future: explore non-linear / ML mapping delivered via FactSet's FPE. Explicitly parked for future exploration. | Not raised. | Hassan: risk team developing enhanced mapping (potentially ML); will need to discuss with FactSet for FPE embedding — 'something we will explore in the future, not now.' | Not re-raised. | Not re-raised. | Not re-raised. Remains parked. | PARKED. Single mention in Apr 13 with explicit deferral language.
Monte Carlo Mac memory failure [topic_002 · CLOSED · HIGH] Mark's CTF-by-account MC Mac job crashed even with one risk metric due to insufficient memory. Memory boost option resolved it — confirmed by PA product team re-running Mark's test job on Apr 13. | Mark's MC Mac job crashed even with 1 risk metric (volatility contribution). Managed services confirmed memory failure in both Batcher and PA. Nick to attack from 3 angles. | RESOLVED. Nick met with PA product team that morning; they ran Mark's test job with memory boost and it completed. | Not re-raised. | Hassan and Mark referenced the memory-boost fix as resolved; ARM viewed as straightforward 'once we address the memory boost issue we talked about.' | Not re-raised. | Apr 13 transcript contains explicit closure: 'they did take Mark's test job and run it and it did complete with the memory boost.' Verifier confirms status=closed.
Resourcing & implementation tracker access [topic_014 · CLOSED · LOW] Charlie Moss assigned as FactSet implementation lead. SWIB-side access to FactSet's implementation tracker confirmed. John McLeanHann to receive network ID. | Charlie Moss assigned. Joins from Apr 13. Apr 7 call cancelled. | Charlie attended first call. SWIB-side tracker access confirmed. Courtney to order John's network ID. | Implementation tracker access in place; focus shifted to Smartsheet alignment (Topic 008). | Not re-raised. | Not re-raised. Remains closed. | CLOSED. Core resourcing decisions completed; only John's network ID remains as an open admin task within an otherwise closed topic.

## Sheet1
Topic | Update
Working group structure & cadence | Four working groups now formally kicked off: SO7, stress test, Snowflake onboarding, ARM. Monday RAM call shortened to a half-hour weekly umbrella sync for cross-stream progress check-ins. SO7 confirmed as the highest-priority stream with weekly cadence. Other streams meet on a rolling basis based on momentum rather than fixed weekly slots. Resource overlap acknowledged — same people may need to focus on one workstream for a whole week.
Project tracking — Smartsheet vs FactSet implementation tracker | as we work through the working groups - we are refinin gthe implmentation plan, will update the group once we have a satisfying overall breakdown + align on updates & follow ups Aligning SWIB's Smartsheet (covering full charter incl. Power BI) with FactSet's implementation tracker (SOW-specific). SWIB tracks at module level; FactSet tracks granular.
WG - Snowflake data shares & environments | Onboarding FactSet Snowflake data shares across SWIB dev/test/UAT/prod environments. Kickoff complete; working group active. Test upload of SO7 output to Snowflake achievable once SWIB-side file specs are finalized. Independent workstream, not blocking SO7.
WG - Aggregated Risk Model (ARM) | SWIB now has the ARM file ready for Nick, but transfer is blocked as file is too large for normal channels and Nick is working on access to an alternate delivery method. Once delivered, FactSet can begin processing and provide feedback. No new content review until file lands.
WG - Stress test & scenario analysis build | Composites received by FactSet. Mark sent three PA files representing the full set. Charlie combined those three into one doc and asked Mark to review each report to confirm correct stress test scenarios — no response yet from Mark. Charlie will ping Mark on the thread. No new action gates; waiting on Mark's review of the combined doc.
WG - SO7 PA build | Charlie has combined three PA docs into one with three sections: SO1 collapsed with Mac model, SO2 collapsed with BARRA model, SO3 expanded with Mac model. Mark sent a sample composite with mixed asset types for running through all reports. Next step is column rationalization: Assess what fields in the current SO7 spec are needed vs. should change. (example:include CLO / CMBS / ABS structural data availability, options Greeks coverage, and factor grouping approach, SO7 is ~75% of what SWIB wants, 25% reserved for FactSet-suggested changes.
Risk model selection — LMAC vs MC Mac vs FV Mac | Which risk model the ARM run will use. LMAC favoured for 3-horizon views; MC Mac was the default but had memory issues now resolved; FV Mac proposed for caching benefits. Drives run efficiency and downstream extensibility to fat-tail / credit-adjusted VaR. No update
Monte Carlo Mac memory failure | Memory boost option resolved it - closed
Standard Operating Procedures for daily EDS / EDS+ load | Framework to be developed in parallel with managed services. Must work for current EDS and forward EDS+ load. Cross-communication needed with RAM workstream so optimization requirements feed in. No update
Fat-tail & credit-adjusted VaR extensions | Future model enhancements beyond the current MC Mac baseline. Credit-adjusted VaR via FactSet's CRYAT team explicitly deferred to a future phase.
Hedge-fund model — MSCI → FactSet mapping | Today: linear MSCI-driven mapping into FactSet. Explicitly parked for future exploration.
Asset Allocation view | A third grouping view (alongside business line + asset class) matching SWIB's actual asset allocation, requiring new composites (AA1, AA2, AA3...) No update
Composite & hierarchy uploads via parser | Daily uploads of business lines, sub-BL, AC1/AC2 composites + ACTMs + benchmarks sourced from UDM. Parser will use 'matching start date' setting for incremental updates. ACTMs already loaded as samples. Replaces SWIB's current monthly 'core aim' manual process. Implicit progress — composites referenced as already received by FactSet for stress test work. No specific parser/hierarchy discussion in this call.

## Anchors lifecycle
Anchor lifecycle — follow-up items and open questions with status tracking
Topic | Type | Item | Owner | Added in | Status | Closed in
Risk model selection — LMAC vs MC Mac vs FV Mac | Follow-up | Hassan: run LMAC vs MC Mac test on fixed-income portfolio (convexity check) | Hassan | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Follow-up | Nick: run FV Mac on fixed-income portfolio path for comparison | Nick | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Follow-up | Nick: risk team to present pro/con analysis of LMAC vs MC Mac vs FV Mac on accuracy + report efficiency | Nick | 2026-04-13 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Open question | Are private markets covered under LMAC? | — | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Open question | Which model is easiest to extend to fat-tail later? | — | 2026-04-02 | OPEN | —
Risk model selection — LMAC vs MC Mac vs FV Mac | Open question | Does FV Mac's caching layer change the memory profile vs MC Mac? | — | 2026-04-02 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | Mark: send SO7 starting document to Nick | Mark | 2026-04-02 | DONE | 2026-04-13
SO7 PA report build (A / B / L) | Follow-up | Charlie: take SO1 + SO3 production docs and build single 'golden source' SO7 doc | Charlie | 2026-04-20 | DONE | 2026-05-18
SO7 PA report build (A / B / L) | Follow-up | Mark: send the SO2 production doc to Charlie | Mark | 2026-04-20 | DONE | 2026-05-18
SO7 PA report build (A / B / L) | Follow-up | Louis: send Nick available times for the SO7 working group | Louis | 2026-04-29 | DONE | 2026-05-18
SO7 PA report build (A / B / L) | Follow-up | Mark + Charlie + Sean: review each report in the combined SO7 doc to confirm correct stress test scenarios | Mark + Charlie + Sean | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | Charlie: provide data coverage check on SO7 columns once SWIB confirms which columns to assess | Charlie | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | Hassan + Mark + Sean: rationalize SO7 column scope — confirm which metrics keep, which to drop, which alternatives FactSet offers | Hassan + Mark + Sean | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | FactSet (Nick + Charlie): document available structural data for CLOs, CMBS, ABS by public CUSIP / ticker | FactSet | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Follow-up | FactSet (Nick + Charlie): document available options Greeks coverage for SO7 | FactSet | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Open question | Which settings inconsistencies between SO1/SO2/SO3 (futures, currencies) must be fixed in the SO7 golden source? | — | 2026-04-13 | OPEN | —
SO7 PA report build (A / B / L) | Open question | Should risk-based performance attribution be dropped from SO7 given MC Mac limitation? | — | 2026-04-13 | OPEN | —
SO7 PA report build (A / B / L) | Open question | What structural data is available in FactSet for CLOs, CMBS, ABS with public identifiers? | — | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Open question | Which Greeks does FactSet provide for options in SO7? | — | 2026-05-18 | OPEN | —
SO7 PA report build (A / B / L) | Open question | If SWIB adds significantly more columns, will SO7 PA jobs still complete or need to be redesigned into multiple tasks? | — | 2026-05-18 | OPEN | —
Stress test & scenario analysis build | Follow-up | Nick: send Hassan the stress test test job file (Mark previously created, was meant to go last week) | Nick | 2026-04-29 | OPEN | —
Stress test & scenario analysis build | Follow-up | Nick: follow up with questions on what's needed to get the stress test set up | Nick | 2026-04-29 | OPEN | —
Stress test & scenario analysis build | Follow-up | Charlie: ping Mark to review the combined stress test doc and confirm scenario alignment | Charlie | 2026-05-18 | OPEN | —
Stress test & scenario analysis build | Follow-up | Mark: review combined stress test doc and confirm each report uses correct scenarios | Mark | 2026-05-18 | OPEN | —
Stress test & scenario analysis build | Open question | Will UDM composites coming over require modifications to current business lines? | — | 2026-04-02 | OPEN | —
Aggregated Risk Model (ARM) — CTF by account contributions | Follow-up | FactSet: provide feedback on ARM PA report sent by SWIB | FactSet | 2026-04-13 | OPEN | —
Aggregated Risk Model (ARM) — CTF by account contributions | Follow-up | Hassan: secure a large-file transfer method and send ARM file to Nick | Hassan | 2026-05-18 | OPEN | —
Composite & hierarchy uploads via parser | Follow-up | Nick + Laura: test parser settings with sample examples before go-live | Nick + Laura | 2026-04-13 | OPEN | —
Composite & hierarchy uploads via parser | Follow-up | Charlie: use already-loaded ACTMs to generate interactive output once SO7 doc is built | Charlie | 2026-04-20 | OPEN | —
Composite & hierarchy uploads via parser | Open question | How are start/end dates for composite membership best structured in the daily file? | — | 2026-04-13 | OPEN | —
Composite & hierarchy uploads via parser | Open question | What templates does FactSet have for ACTM required fields and frequencies? | — | 2026-04-13 | OPEN | —
Snowflake data shares & environments | Follow-up | Nick: leverage product team alongside himself + Charlie for SWIB-side Snowflake connectivity | Nick | 2026-04-13 | OPEN | —
Snowflake data shares & environments | Follow-up | Hassan: kick off introductory architecture discussion between teams | Hassan | 2026-04-29 | DONE | 2026-05-18
Snowflake data shares & environments | Follow-up | Louis: include 'when can FactSet push to Snowflake' in Smartsheet tracking | Louis | 2026-04-20 | OPEN | —
Snowflake data shares & environments | Open question | Incremental delivery vs waterfall — wait until all data is ready, or push as it stabilizes? | — | 2026-04-20 | OPEN | —
Project tracking — Smartsheet vs FactSet implementation tracker | Follow-up | Louis: meet with Anand to finalize Smartsheet structure | Louis | 2026-04-20 | OPEN | —
Project tracking — Smartsheet vs FactSet implementation tracker | Follow-up | Louis: send first draft of Smartsheet to FactSet by EOD Tuesday after Apr 20 | Louis | 2026-04-20 | OPEN | —
Project tracking — Smartsheet vs FactSet implementation tracker | Follow-up | FactSet: replicate SWIB's high-level topics in implementation tracker after receiving Smartsheet draft | FactSet (Nick) | 2026-04-20 | OPEN | —
Working group structure & cadence | Follow-up | Louis + Hassan: discuss RAM sponsor meeting cadence offline | Louis + Hassan | 2026-04-20 | OPEN | —
Working group structure & cadence | Open question | How often should the RAM sponsor meeting run? | — | 2026-04-20 | OPEN | —
Standard Operating Procedures for daily EDS / EDS+ load | Follow-up | Nick: ensure managed services receives heads-up on what's being built EDS-side | Nick | 2026-04-13 | OPEN | —
Standard Operating Procedures for daily EDS / EDS+ load | Follow-up | Hassan: share SOP framework with FactSet as it develops | Hassan | 2026-04-13 | OPEN | —
Standard Operating Procedures for daily EDS / EDS+ load | Open question | What rerun protocols must be in place for the EDS+ data going live? | — | 2026-04-13 | OPEN | —
Asset Allocation view (third hierarchy) | Open question | Should the Asset Allocation view be in this run or the next run? | — | 2026-04-02 | OPEN | —
Fat-tail & credit-adjusted VaR extensions | Open question | When should fat-tail modeling be revisited and what project milestone triggers the conversation? | — | 2026-04-02 | OPEN | —
Hedge-fund model — MSCI → FactSet mapping | Open question | How will SWIB's enhanced hedge-fund mapping be embedded into FactSet — via FPE or another mechanism? | — | 2026-04-13 | OPEN | —
Monte Carlo Mac memory failure | Follow-up | Mark: send PA document to Nick for memory issue investigation | Mark | 2026-04-02 | DONE | 2026-04-02
Monte Carlo Mac memory failure | Follow-up | Nick: attack memory issue from 3 angles — setup change, alternate model, memory boost | Nick | 2026-04-02 | DONE | 2026-04-13
Resourcing & implementation tracker access | Follow-up | Courtney: order John McLeanHann a network ID for tracker access | Courtney | 2026-04-13 | OPEN | —
Resourcing & implementation tracker access | Follow-up | Nick: send Louis the tracker link (workstation + web access) | Nick | 2026-04-13 | DONE | 2026-04-13

## Decisions log
Decisions log — every locked decision across all calls
Topic | Decision | Decided in
Aggregated Risk Model (ARM) — CTF by account contributions | Aggregation across business lines / sub-BL / AC1-AC3 happens in Snowflake, NOT FactSet | 2026-04-02
Resourcing & implementation tracker access | Charlie Moss assigned by FactSet professional services as implementation lead | 2026-04-02
Resourcing & implementation tracker access | Apr 7 call cancelled to give Charlie prep time; weekly cadence resumes Apr 13 | 2026-04-02
Monte Carlo Mac memory failure | Memory boost resolves the MC Mac memory failure for Mark's test case | 2026-04-13
Composite & hierarchy uploads via parser | Parser will use 'matching start date' setting — incremental updates, not full overwrite. Rejoining a composite creates a second start-date entry. | 2026-04-13
Fat-tail & credit-adjusted VaR extensions | Credit-adjusted VaR and fat-tail extensions are deferred to a future phase (post-platform-establishment) | 2026-04-13
SO7 PA report build (A / B / L) | SO1→SO7A, SO2→SO7B, SO3→SO7L naming confirmed | 2026-04-20
Snowflake data shares & environments | Data delivery to Snowflake happens AFTER PA engine output is validated; flat-file structure stabilizes first | 2026-04-20
Project tracking — Smartsheet vs FactSet implementation tracker | SWIB Smartsheet stays one or two levels above FactSet tracker. SWIB tracks ARM / stress test / portfolio risk analytics at module level; FactSet stays granular. | 2026-04-20
SO7 PA report build (A / B / L) | SO7 is the priority workstream — gets a dedicated weekly working group | 2026-04-29
SO7 PA report build (A / B / L) | Working group attendees: Mark, Sonon, Laura, Louis | 2026-04-29
Stress test & scenario analysis build | Hold off on a dedicated stress test working group — wait for Charlie's feedback first | 2026-04-29
Aggregated Risk Model (ARM) — CTF by account contributions | Hold off on dedicated ARM working group — wait for FactSet feedback first | 2026-04-29
Snowflake data shares & environments | Hassan to kick off introductory architecture discussion soon — independent workstream, won't block SO7 | 2026-04-29
Working group structure & cadence | Monday RAM weekly call stays as umbrella sync | 2026-04-29
Working group structure & cadence | SO7 working group gets a fixed weekly slot; others are ad-hoc | 2026-04-29
Working group structure & cadence | Each working group has an initial full-group kickoff meeting to agree direction, then splits off | 2026-04-29
SO7 PA report build (A / B / L) | Sean Won added to the SO7 working group | 2026-05-18
SO7 PA report build (A / B / L) | Current SO7 spec represents ~75% of final scope — 25% reserved for FactSet-suggested additions/changes (CLO/CMBS/ABS structural data, options Greeks, factor grouping) | 2026-05-18
Working group structure & cadence | Four working groups formally kicked off: SO7, stress test, Snowflake onboarding, ARM | 2026-05-18
Working group structure & cadence | Monday RAM weekly call shortened to half an hour as a cross-stream umbrella sync | 2026-05-18
Working group structure & cadence | Non-SO7 working groups meet on momentum-based cadence (not fixed weekly) until they have substantive updates | 2026-05-18

## Key terms registry
Key terms registry — anchor for matcher + RAG retrieval queries
ID | Topic | Key terms | Term count
topic_001 | Risk model selection — LMAC vs MC Mac vs FV Mac | LMAC, MC Mac, FV Mac, Monte Carlo, fair value Mac, fixed income convexity, Hassan, Nick, risk model, short term medium term long term | 10
topic_003 | SO7 PA report build (A / B / L) | SO7, SO7A, SO7B, SO7L, SO1, SO2, SO3, golden source, Charlie, factor groupings, risk-based performance attribution, wish list, Sean Won, CLO, CMBS, ABS, options Greeks, effective duration, coverage check | 19
topic_004 | Stress test & scenario analysis build | stress test, scenario analysis, monthly run, CTF business line factors, test job, Mark | 6
topic_005 | Aggregated Risk Model (ARM) — CTF by account contributions | ARM, aggregated risk model, CTF, VTF, SMF, account contributions, Snowflake aggregation, business line sub-business line AC1 AC2 AC3, ExPost, EMAC | 10
topic_006 | Composite & hierarchy uploads via parser | composite, hierarchy, parser, ACTM, benchmarks, UDM, start date, end date, matching start date, core aim, daily upload, Laura | 12
topic_007 | Snowflake data shares & environments | Snowflake, data shares, dev test UAT prod, environments, architecture team, Anand, data engineering, waterfall | 8
topic_008 | Project tracking — Smartsheet vs FactSet implementation tracker | Smartsheet, implementation tracker, charter, Power BI, module level, Louis, Anand | 7
topic_009 | Working group structure & cadence | working group, RAM weekly call, Monday call, sponsor meeting, ad hoc, deep dive | 6
topic_010 | Standard Operating Procedures for daily EDS / EDS+ load | SOP, standard operating procedures, EDS, EDS+, rerun protocol, managed services, daily load | 7
topic_011 | Asset Allocation view (third hierarchy) | asset allocation view, AA1, AA2, AA3, third hierarchy, Anand | 6
topic_012 | Fat-tail & credit-adjusted VaR extensions | fat-tail, credit-adjusted VaR, CRYAT team, MC Mac extension | 4
topic_013 | Hedge-fund model — MSCI → FactSet mapping | hedge fund, MSCI, FactSet mapping, FPE, non-linear, machine learning | 6
topic_002 | Monte Carlo Mac memory failure | MC Mac, memory, memory boost, Batcher, PA, volatility contribution, managed services, Mark | 8
topic_014 | Resourcing & implementation tracker access | Charlie Moss, professional services, implementation tracker, John McLeanHann, network ID, Courtney | 6

## Status review
Status review — stale-topic & integrity flags for human decision
Topic | Current status | Last touched | Calls silent | Recommendation
Risk model selection — LMAC vs MC Mac vs FV Mac | OPEN | 2026-04-29 | 1 | Silent 1 call — likely active, no action.
SO7 PA report build (A / B / L) | OPEN | 2026-05-18 | 0 | Active in latest call — no action.
Stress test & scenario analysis build | OPEN | 2026-05-18 | 0 | Active in latest call — no action.
Aggregated Risk Model (ARM) — CTF by account contributions | OPEN | 2026-05-18 | 0 | Active in latest call — no action.
Composite & hierarchy uploads via parser | OPEN | 2026-04-29 | 1 | Silent 1 call — likely active, no action.
Snowflake data shares & environments | OPEN | 2026-05-18 | 0 | Active in latest call — no action.
Project tracking — Smartsheet vs FactSet implementation tracker | OPEN | 2026-04-20 | 2 | FLAG: Silent 2 calls. Confirm still active or park.
Working group structure & cadence | OPEN | 2026-05-18 | 0 | Active in latest call — no action.
Standard Operating Procedures for daily EDS / EDS+ load | OPEN | 2026-04-13 | 3 | FLAG: Silent 3 calls. Strong candidate for park or close.
Asset Allocation view (third hierarchy) | PARKED | 2026-04-02 | 4 | Parked, silent 4 call(s) — keep parked unless explicitly revived.
Fat-tail & credit-adjusted VaR extensions | PARKED | 2026-04-13 | 3 | Parked, silent 3 call(s) — keep parked unless explicitly revived.
Hedge-fund model — MSCI → FactSet mapping | PARKED | 2026-04-13 | 3 | Parked, silent 3 call(s) — keep parked unless explicitly revived.
Monte Carlo Mac memory failure | CLOSED | 2026-04-29 | 1 | Closed — no action needed.
Resourcing & implementation tracker access | CLOSED | 2026-04-20 | 2 | Closed — no action needed.